## Year 1
PhD - First year | Fall 2024 |  |  |  |  | Winter 2025 |  |  |  | Spring-Summer 2025
| Sep |  | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul |  | Aug
Task
Professionnal
TA (Biostats)
Grants & scholarships application
Conference & Networking
Program
Proposal - Submission | [12 empty] | TRUE
Comprehensive exam | [15 empty] | TRUE
TAC meeting | [7 empty] | TRUE
Research
Proposal - Litterature review
Proposal - Writing (Thesis introduction)
MSc Project (Paper 1) - Finish analysis
MSc Project (Paper 1) - Writing
MSc Project (Paper 1) - Manuscript submission | [14 empty] | TRUE
Field season
Working on it
| TRUE | Deadline
[

## Year 2
PhD - Second year | Fall 2025 |  |  |  |  | Winter 2026 |  |  |  | Spring-Summer 2026
| Sep |  | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug
Task
Professionnal
TA (TBD)
TA (TBD)
Grants & scholarships application
Conference & Networking
Honors student supervision
Program
Class (TBD)
TAC meeting | [7 empty] | TRUE
Research
Chapter 1 (Paper 2) - Analysis
Chapter 1 (Paper 2) - Writing
Chapter 1 (Paper 2) - Manuscript submission | [13 empty] | TRUE
Chapter 2 (Paper 3) - Analysis
Field season
Working on it
| TRUE | Deadline

## Year 3
PhD - Third year | Fall 2026 | [5 empty] | Winter 2027 |  |  |  | Spring-Summer 2027
| Sep |  | Oct | Nov | Dec |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug
Task
Professionnal
TA (TBD)
TA (TBD)
Grants & scholarships application
Conference & Networking
Honors student supervision
Program
TAC meeting | [8 empty] | TRUE
Research
Chapter 2 (Paper 3) - Analysis
Chapter 2 (Paper 3) - Writing
Chapter 2 (Paper 3) - Manuscript submission | [5 empty] | TRUE
Chapter 3 (Paper 4) - Analysis
Chapter 3 (Paper 4) - Writing
Field season
Working on it
| TRUE | Deadline

## Year 4
PhD - Fourth year | Fall 2027 |  |  |  |  | Winter 2028 |  |  |  |  | Spring-Summer 2028
| Sep |  | Oct | Nov | Dec | Jan | Feb | Mar |  | Apr | May | Jun | Jul |  | Aug
Task
Professionnal
TA (TBD)
TA (TBD)
Grants & scholarships application
Conference & Networking
Program
Thesis submission | [13 empty] | TRUE
TAC meeting | [8 empty] | TRUE
Thesis defence | [15 empty] | TRUE
Research
Chapter 3 (Paper 4) - Manuscript submission | TRUE
Chapter 4 (Paper 5) - Analysis
Chapter 4 (Paper 5) - Writing
Chapter 4 (Paper 5) - Manuscript submission | [10 empty] | TRUE
Thesis writing (General discussion)
Working on it
| TRUE | Deadline