## Year 1
PhD - First year | Fall 2024 |  |  |  |  | Winter 2025 |  |  |  | Spring-Summer 2025
| Sep |  | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul |  | Aug
Task
Professionnal
TA (Biostats)
Grants & scholarships application
Conference & Networking
Program
Proposal - Submission | [12 empty] | TRUE
Comprehensive exam | [15 empty] | TRUE
TAC meeting | [7 empty] | TRUE
Research
Proposal - Litterature review
Proposal - Writing (Thesis introduction)
MSc Project (Paper 1) - Finis analysis
Paper 1 - Writing
Paper 1 - Manuscript submission | [14 empty] | TRUE
Field season
Working on it
| TRUE | Deadline
[

## Year 2
PhD - Second year | Fall 2025 |  |  |  |  | Winter 2026 |  |  |  | Spring-Summer 2026
| Sep |  | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug
Task
Professionnal
TA (TBD)
TA (TBD)
Grants & scholarships application
Conference & Networking
Honors student supervision
Program
Class (TBD)
TAC meeting | [7 empty] | TRUE
Research
Chapter 1 - Analysis
Chapter 1 - Writing (Paper 2)
Paper 2 - Manuscript submission | [13 empty] | TRUE
Chapter 2 - Analysis
Field season
Working on it
| TRUE | Deadline

## Year 3
PhD - Third year | Fall 2026 | [5 empty] | Winter 2027 |  |  |  | Spring-Summer 2027
| Sep |  | Oct | Nov | Dec |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug
Task
Professionnal
TA (TBD)
TA (TBD)
Grants & scholarships application
Conference & Networking
Honors student supervision
Program
TAC meeting | [8 empty] | TRUE
Research
Chapter 2 - Analysis
Chapter 2 - Writing (Paper 3)
Paper 3 - Manuscript submission | [5 empty] | TRUE
Chapter 3 - Analysis
Chapter 3 - Writing (Paper 4)
Field season
Working on it
| TRUE | Deadline

## Year 4
PhD - Fourth year | Fall 2027 |  |  |  |  | Winter 2028 |  |  |  |  | Spring-Summer 2028
| Sep |  | Oct | Nov | Dec | Jan | Feb | Mar |  | Apr | May | Jun | Jul |  | Aug
Task
Professionnal
TA (TBD)
TA (TBD)
Grants & scholarships application
Conference & Networking
Program
Thesis submission | [13 empty] | TRUE
TAC meeting | [8 empty] | TRUE
Thesis defence | [15 empty] | TRUE
Research
Paper 4 - Manuscript submission | TRUE
Chapter 4 - Analysis
Chapter 4 - Writing (Paper 5)
Paper 5 - Manuscript submission | [10 empty] | TRUE
Thesis writing (General discussion)
Working on it
| TRUE | Deadline